## Instructions
PMO portfolio workbook - ProjectPulse import
Fill one row per record. Dark blue headers are required, light blue are optional. Keep the sheet names and headers as they are. Dates: YYYY-MM-DD.
Sheet | Column | Required | Allowed values / notes
Projects |  |  | The project register: one row per project. Maintained by: PMO.
| Project Name | Yes
| Description | No
| Project Manager | Yes | Name exactly as on the Employees sheet.
| Department | Yes | Owning department.
| Start Date | Yes
| Planned End Date | Yes
| Actual End Date | No | Fill in only when the project is finished.
| Budget | Yes | Approved budget, in dollars.
| Actual Cost to Date | Yes | From Finance. Total spent so far.
| Status | Yes | On Track, At Risk, Delayed, Completed, On Hold. The status the PM reports. The dashboard also computes its own.
| Priority | Yes | Critical, High, Medium, Low
Risks |  |  | The RAID log: one row per risk. Maintained by: Project managers.
| Risk ID | No
| Project | Yes
| Category | Yes | e.g. Schedule, Budget, Scope, Technical, Resource, Vendor, Security, Compliance
| Description | Yes
| Probability | Yes | 1 (rare) to 5 (almost certain).
| Impact | Yes | 1 (minor) to 5 (severe).
| Owner | Yes | Name as on the Employees sheet.
| Status | Yes | Open, Mitigating, Closed, Accepted
| Date Raised | Yes
| Date Closed | No
| Mitigation % | No | How far the mitigation plan has got. 40% or 40. Blank = 0.
Ceremonies |  |  | Planning, stand-ups, reviews and retros. Optional. Maintained by: Scrum masters. (whole sheet optional)
| Project | Yes
| Sprint | No
| Ceremony Type | Yes | Sprint Planning, Daily Standup, Sprint Review, Retrospective
| Date | Yes
| Attendance % | Yes | Share of the team who attended. 85% or 85.
| Duration (min) | Yes
| Action Items | No | Blank = 0.
Archive |  |  | Closed projects with known outcomes, used to train the delay model. Optional. Maintained by: PMO. (whole sheet optional)
| Project Code | Yes
| Department | Yes
| Close Year | Yes
| Budget Utilization | Yes | AC ÷ EV at the mid-project snapshot.
| Open Risks | Yes
| Avg Resource Utilization | Yes | e.g. 0.95
| Sprint Velocity | Yes | Average SP of the last 3 sprints.
| Tasks Remaining | Yes
| Delayed | Yes | Yes, No. Did the project finish after its planned end date?

## Projects
Project Name | Description | Project Manager | Department | Start Date | Planned End Date | Actual End Date | Budget | Actual Cost to Date | Status | Priority
Note on C1: Name exactly as on the Employees sheet.
Note on D1: Owning department.
Note on G1: Fill in only when the project is finished.
Note on H1: Approved budget, in dollars.
Note on I1: From Finance. Total spent so far.
Note on J1: The status the PM reports. The dashboard also computes its own.
Note on K1: Critical, High, Medium, Low

## Risks
Risk ID | Project | Category | Description | Probability | Impact | Owner | Status | Date Raised | Date Closed | Mitigation %
Note on C1: e.g. Schedule, Budget, Scope, Technical, Resource, Vendor, Security, Compliance
Note on E1: 1 (rare) to 5 (almost certain).
Note on F1: 1 (minor) to 5 (severe).
Note on G1: Name as on the Employees sheet.
Note on H1: Open, Mitigating, Closed, Accepted
Note on K1: How far the mitigation plan has got. 40% or 40. Blank = 0.

## Ceremonies
Project | Sprint | Ceremony Type | Date | Attendance % | Duration (min) | Action Items
Note on C1: Sprint Planning, Daily Standup, Sprint Review, Retrospective
Note on E1: Share of the team who attended. 85% or 85.
Note on G1: Blank = 0.

## Archive
Project Code | Department | Close Year | Budget Utilization | Open Risks | Avg Resource Utilization | Sprint Velocity | Tasks Remaining | Delayed
Note on D1: AC ÷ EV at the mid-project snapshot.
Note on F1: e.g. 0.95
Note on G1: Average SP of the last 3 sprints.
Note on I1: Did the project finish after its planned end date?